SIGHT MANAGER

How to Use Guide

A practical guide for site managers and administrators

# Getting Started

Sight Manager is accessed via your web browser at sight-manager.vercel.app. It works on desktop, tablet, and mobile. Log in with your email and password.

## Your First Morning

When you arrive on site, your first stop should always be the Daily Brief. Here is how to get there:

1. Log in and select your site from the site selector dropdown

2. Click Daily Brief in the left sidebar

3. Review the stats bar at the top — it shows everything needing attention today

4. Work through each section from top to bottom

TIP: The Daily Brief is your command centre. Everything flows from here — orders, deliveries, contractor confirmations, inactive plots.

# Starting a Job

You can start a job from multiple places: the Walkthrough, the Daily Brief, the Programme, or the Plot Detail page. No matter where you click Start, the same flow runs:

## Step 1: Order Check

If the job has materials that haven't been ordered or delivered, you will see a warning with 3 options:

Option A: Start today — resolve orders now

You will step through each supplier and either Mark Sent, Send Order (opens an email), or mark as On Site. All orders must be resolved before continuing.

Option B: Pick a start date

Choose a future date. The programme will shift to match — all subsequent jobs and orders cascade automatically.

Option C: Start anyway

Orders stay as they are. They will appear on your Daily Brief under Orders to Place so you can handle them when ready.

## Step 2: Schedule Impact

If the job is starting earlier or later than planned, you will see a schedule impact dialog:

Starting Early

Pull Programme Forward — moves this job and all downstream jobs earlier.

Expand This Job — starts now but keeps the original end date. Programme stays put.

Pull to Next Event — shifts to align with the nearest upcoming delivery or job start.

Starting Late

Push Programme — shifts everything downstream later.

Compress Duration — starts today, shortens the job to fit the original end date.

TIP: All shifts use working days (Monday to Friday). Weekends are automatically skipped. The delay input box explicitly says "working days (Mon-Fri)".

# Completing and Signing Off a Job

Complete and Sign Off are two separate steps:

## Completing a Job

1. Click Complete on the job (from walkthrough, programme, or plot detail)

2. The Post-Completion Dialog appears showing how far ahead or behind you are

3. If the next job has undelivered orders, resolve them first

4. If a contractor is assigned and you are ahead of schedule, confirm their availability

5. Choose what happens next: Start today, Start Monday, Push forward, or Leave for now

TIP: If you are not ready to confirm the contractor, click "Confirm later — add to Daily Brief". The plot goes inactive and appears in the Contractor Confirmations section.

## Signing Off a Job

1. Click Sign Off Job (red button in walkthrough or programme)

2. Add optional sign-off notes and photos

3. Click Confirm Sign Off

Sign-off is the quality approval. When you sign off, any ORDERED materials for that job are automatically marked as DELIVERED (materials confirmed used on site).

# Managing Orders

The Daily Brief is your hub for the full order lifecycle:

## Orders to Place

These are orders that should have been sent to suppliers. For each one you can:

1. Send Order — opens a pre-formatted email to the supplier with all items and quantities

2. Mark Sent — if you have already placed the order by phone or another method

TIP: If you chose "Start anyway" when starting a job, the orders will appear here. Send them when you are ready.

## Upcoming Deliveries

Orders that have been sent and are awaiting delivery. For each one:

1. Check the expected delivery date — use the date picker to change it if the supplier gave a different date

2. When materials arrive, click Received to mark them as delivered

TIP: Changing the delivery date here updates the order record. The programme dots on the Gantt will update to match.

# Using the Programme (Gantt Chart)

## View Modes

Jobs — shows parent stage bars (e.g. Groundworks) that aggregate from their sub-jobs. Click to expand.

Sub-Jobs — shows every individual task bar (e.g. Foundations, DPC, Oversite, Drainage).

Week / Day — toggle between weekly and daily column views. Day view shows Mon-Fri with day names and greyed weekends.

## Overlay Mode

Current — shows where jobs are now after any shifts.

Original — shows where jobs were originally planned.

Overlay — shows both, with ghost bars (dashed lines) showing the original plan behind the current bars.

## Delaying a Job

1. Click on a job bar to open its detail panel

2. Click Delay / Push Job

3. Enter the number of working days to delay

4. Select a reason (Rain, Temperature, or Other)

5. Click Delay — the job and all downstream jobs shift by that many working days

TIP: The input box allows you to clear it and type freely. The label says "working days (Mon-Fri)" so you know weekends are excluded.

## Bulk Actions

1. Click Select in the toolbar

2. Tick the plots you want to action

3. Use the floating bar at the bottom: Start All, Delay Jobs, or Cancel

Start All triggers the full pre-start flow for each selected plot's next job. You will see order and schedule dialogs for each one.

# Site Walkthrough

The Walkthrough is designed for site managers walking the site plot by plot.

1. Navigate to your site and click Site Walkthrough in the sidebar

2. You will see the first plot with its current job and next job

3. Swipe left/right or use the arrows to move between plots

4. For each plot you can: Start the next sub-job, Sign Off the current job, Add photos/notes/snags, or Delay

The walkthrough button always shows the sub-job name (e.g. "Start Foundations") not a generic "Start Job".

TIP: Every action from the walkthrough goes through the same centralised flow as everywhere else — order checks, predecessor checks, cascade dialogs.

# Inactive Plots

An inactive plot is one with no jobs currently in progress. The Daily Brief shows these in the Inactive Plots section with a label explaining why:

Not Started — no work has begun yet on this plot.

Deferred — you chose "Leave for now" after completing a job. Restart when ready.

Awaiting contractor — you chose "Confirm later" on the contractor step. Contact the contractor and confirm from the Daily Brief.

Awaiting materials — the next job has undelivered orders. Materials need to arrive first.

Next: [job name] — ready to start the next job. Click the Start button to begin.

TIP: Each inactive plot has a Start button that goes through the full pre-start flow. You do not need to navigate to the walkthrough or plot detail — you can start directly from the Daily Brief.

# Contractor Confirmations

When you sign off a job and the next job has a contractor assigned, and you are ahead of schedule, you will be asked to confirm the contractor is available.

If you are not ready to confirm, click "Confirm later — add to Daily Brief". This creates an entry in the Awaiting Contractor Confirmation section of the Daily Brief.

From the Daily Brief, you can:

1. Call — tap to phone the contractor directly

2. Email — open an email to the contractor

3. Confirmed — Start Job — the contractor is available, start the job (full pre-start flow runs)