SIGHT MANAGER

System Flow Schematic

Technical reference for how every flow works end-to-end

April 2026  —  Confidential

# 1. Job Lifecycle Flow

Every job follows this exact lifecycle. Each transition has specific side effects that are enforced by the server.

NOT_STARTED  →  IN_PROGRESS  →  COMPLETED  →  SIGNED OFF

## Transition Side Effects

| Action | New Status | Fields Set | Order Effects |
| --- | --- | --- | --- |
| start | IN_PROGRESS | actualStartDate, buildCompletePercent | PENDING → ORDERED (unless skip) |
| complete | COMPLETED | actualEndDate, buildCompletePercent | No order changes |
| signoff | stays COMPLETED | signedOffAt, signedOffById | ORDERED → DELIVERED (auto) |

Complete and Sign-off are SEPARATE actions. A job can be completed but not yet signed off. Sign-off is the explicit approval step that confirms materials have been used.

# 2. Pre-Start Flow (Centralised Hook)

EVERY start button on EVERY screen goes through this identical flow. The useJobAction hook is the single entry point — no exceptions.

## Entry Points

Walkthrough, Daily Brief (Late Starts, Inactive Plots), Plot Detail, Job Detail, Programme Panel (parent + child), Plot Todo List, Contractor Day Sheets, Programme Bulk Start All

## Flow Steps

→  1. User clicks Start (from ANY screen) → triggerJobAction called

→  2. If orders not provided → auto-fetch from /api/jobs/{id}

→  3. Check predecessors (by DATE, not sortOrder)

→     └ If incomplete predecessor exists → show warning dialog

→  4. Check undelivered orders → if any exist → show 3-option dialog:

→     ├ Option A: Resolve orders now → per-supplier resolution (Mark Sent / Send Order / On Site)

→     ├ Option B: Pick a start date → date picker → cascade to match

→     └ Option C: Start anyway → skipOrderProgression flag → orders stay PENDING

→  5. After resolution: if orders ORDERED (not DELIVERED) → target = delivery date, not today

→  6. Check early/late start:

→     ├ Early: Pull Programme Forward / Expand This Job / Pull to Next Event

→     ├ Late: Push Programme / Compress Duration / Backdate

→     └ On time: start immediately

→  7. Cascade runs (if pull forward or push back chosen)

→  8. Job starts → all side effects execute

# 3. Order Lifecycle

PENDING  →  ORDERED  →  DELIVERED   (+ CANCELLED at any point)

## Status Triggers

| Trigger | From | To | Notes |
| --- | --- | --- | --- |
| Job Start (normal) | PENDING | ORDERED | Auto unless skipOrderProgression |
| Job Start ("start anyway") | PENDING | stays PENDING | User handles manually via Daily Brief |
| Job Complete | — | — | No order changes |
| Job Sign Off | ORDERED | DELIVERED | Auto-delivered on sign-off |
| User "Send Order" | PENDING | ORDERED | Opens ASAP email + marks ORDERED |
| User "On Site" | Any | DELIVERED | Manual confirmation |
| Cascade | — | — | Only dates shift, status unchanged |

## Daily Brief Order Pipeline

→  1. Orders to Place (PENDING, due today) → Send Order email / Mark Sent

→  2. Upcoming Orders (PENDING, future) → Same actions

→  3. Upcoming Deliveries (ORDERED) → Change Date / Mark Delivered

→  4. Deliveries Today (ORDERED, due today) → Mark Delivered

→  5. Overdue Deliveries (ORDERED, past due) → Mark Delivered

# 4. Cascade System

ALL schedule shifts use working days (Mon-Fri). Weekends are automatically skipped. Job durations stay as calendar days.

## Pull Forward (Starting Early)

→  Shift triggering job startDate AND endDate by working days

→  Shift ALL jobs on same plot starting at or after triggering job

→  Shift ALL non-cancelled order dates on affected jobs

→  Cap all dates at today — never into past, snap to working day

→  Preserve originalStartDate/originalEndDate on FIRST shift only

→  Orders landing on weekends snap to Friday

## Push Back (Delay)

→  Shift triggering job endDate (and startDate if NOT_STARTED)

→  Shift ALL subsequent jobs (higher sortOrder only)

→  Delay input shows "working days (Mon-Fri)" explicitly

→  Same order shifting and original preservation rules

# 5. Post-Completion Flow

Triggered after every job complete or sign-off. Guides the user through what happens next.

## Steps

→  1. Summary: job name, days ahead/behind, next job preview

→  2. Order Resolution (if next job has undelivered orders):

→     Per supplier: Confirmed on site / Email supplier / Place order now

→  3. Contractor Check (if contractor assigned AND ahead of schedule):

→     ├ Email contractor to request early start

→     ├ Contractor confirmed — pull programme forward

→     ├ Contractor confirmed — keep programme as is

→     └ Confirm later — add to Daily Brief (plot goes inactive)

→  4. Decision:

→     ├ Start today & pull forward → cascade entire programme

→     ├ Start next Monday → schedule for Monday

→     ├ Push forward by X weeks → delay programme

→     └ Leave for now → plot goes inactive ("Deferred")

# 6. Inactive Plots

Plot with NO IN_PROGRESS jobs AND NOT all completed.

| Type | Condition | Label | Badge |
| --- | --- | --- | --- |
| awaiting_contractor | awaitingContractorConfirmation = true | Awaiting contractor for [job] | Orange |
| deferred | awaitingRestart = true | Deferred | Amber |
| awaiting_materials | Completed jobs + undelivered orders | Awaiting materials for [job] | Red |
| awaiting_next | Completed jobs, no material issues | Next: [job name] | Blue |
| not_started | No jobs completed | Not started | Grey |

All start buttons go through full triggerJobAction flow. Both awaitingRestart and awaitingContractorConfirmation cleared on job start.

# 7. Jobs as Containers

→  Parent jobs: parentStage = null, have stageCode (e.g. "Groundworks")

→  Sub-jobs: parentStage = parent's stageCode (e.g. "Foundations", "DPC")

→  You never "start a job" — you start a sub-job

→  Programme Jobs view: synthetic parent bars aggregate from children

→  Programme Sub-Jobs view: individual sub-job bars

→  Parent bar spans min(child.startDate) → max(child.endDate)

→  Walkthrough shows first actionable sub-job, button says "Start [sub-job name]"

# 8. Data-to-View Map

When changing any entity, check ALL views that consume it.

## Order Status Consumers

| View | What It Uses |
| --- | --- |
| Cash Flow Report | ORDERED = committed spend, DELIVERED = actual spend |
| Budget Report | DELIVERED = delivered costs vs budget |
| Supplier Performance | Only DELIVERED orders counted for on-time rate |
| Daily Brief | Orders to Place, Awaiting Delivery, Overdue, Due Today |
| Programme/Gantt | Order dots by status on calendar dates |
| Contractor Share Page | On Site = DELIVERED orders |

## Job Status Consumers

| View | What It Uses |
| --- | --- |
| Programme/Gantt | Bar colours, completion %, parent aggregation |
| Walkthrough | Current job, next job, schedule badge |
| Daily Brief | Starting, finishing, late, overdue, inactive plots |
| Plot Detail | Overview stats, gantt, jobs list, progress |
| Heatmap | buildCompletePercent, RAG status |
| Analytics | Job status breakdown, durations, performance |